## Checklist
Site 2 Service Block Demo Checklist
Use this sheet during the live Site 2 demo. Each row maps to one test item from the adapted Service Block flow.
Observed Test Result and Success? have been pre-filled from the combined live validation dated 2026-03-23. Update only if a newer live demo result differs.
Service Block | Hotseat | Area | Test Item | Device / Target | Purpose | Command / Action | Expected Result / Success Criteria | Observed Test Result | Success? | Notes
SB1 | Hotseat 1 | Remote Access | SSH to C2IdM1 | C2IdM1 | Prove the primary Company 2 identity node is reachable from the approved Site 2 admin path. | ssh ofdengiz@172.30.65.66 hostname | hostname returns c2idm1 | SSH succeeded; hostname returned c2idm1. | PASS | Validated read-only through the Ubuntu jump.
SB1 | Hotseat 1 | Remote Access | SSH to C2IdM2 | C2IdM2 | Prove the secondary Company 2 identity node is reachable from the approved Site 2 admin path. | ssh ofdengiz@172.30.65.67 hostname | hostname returns c2idm2 | SSH succeeded; hostname returned c2idm2. | PASS | Validated read-only through the Ubuntu jump.
SB1 | Hotseat 1 | Remote Access | SSH to C2FS | C2FS | Prove the Company 2 file server is reachable from the approved Site 2 admin path. | ssh odengiz@172.30.65.68 hostname | hostname returns c2fs | SSH succeeded; hostname returned c2fs. | PASS | Validated read-only through the Ubuntu jump.
SB1 | Hotseat 1 | Remote Access | SSH to C2LinuxClient | C2LinuxClient | Prove the Company 2 Linux client is reachable from the approved Site 2 admin path. | ssh odengiz@172.30.65.70 hostname | hostname returns c2linuxclient | SSH succeeded; hostname returned c2linuxclient. | PASS | Validated read-only through the Ubuntu jump.
SB1 | Hotseat 1 | Remote Access | RDP listener on Jump64 | Jump64 | Show the Windows jump host is reachable for GUI-oriented Site 2 validation. | nc -zvw5 172.30.65.178 3389 | connection succeeded | TCP 3389 on 172.30.65.178 succeeded from the Ubuntu jump. | PASS | Used as the approved Windows demo path.
SB1 | Hotseat 1 | DHCP | C2 DHCP primary service state | C2IdM1 | Show the primary Company 2 DHCP service is active. | systemctl is-active isc-dhcp-server | active | isc-dhcp-server returned active on C2IdM1. | PASS | Read-only service-state check.
SB1 | Hotseat 1 | DHCP | C2 DHCP secondary service state | C2IdM2 | Show the secondary Company 2 DHCP service is active. | systemctl is-active isc-dhcp-server | active | isc-dhcp-server returned active on C2IdM2. | PASS | Read-only service-state check.
SB1 | Hotseat 1 | Account Administration | C2 Samba AD replication summary | C2IdM1 and C2IdM2 | Show Company 2 directory replication is healthy on both identity nodes. | samba-tool drs showrepl | 0 consecutive failure(s) | Replication output showed successful neighbors with 0 consecutive failure(s). | PASS | Observed on both Company 2 identity nodes.
SB1 | Hotseat 1 | Account Administration | C2 Samba user and group inventory | C2IdM1 | Show required tenant users and the C2 file access group already exist. | samba-tool user list samba-tool group list | admin, employee1, employee2, c2_file_users present | User list contained Administrator, admin, employee1, and employee2. Group list contained c2_file_users. | PASS | Read-only tenant identity proof.
SB1 | Hotseat 1 | Account Administration | C1 internal web namespace resolution summary | C2LinuxClient | Show the Linux client can resolve the core internal web namespace used in the main demo. | nslookup c1-webserver.c1.local | c1-webserver.c1.local resolves with dual A records | c1-webserver.c1.local resolved to 172.30.64.162 and 172.30.65.162. | PASS | Keeps the demo on the core internal HTTPS proof path.
SB1 | Hotseat 2 | Remote Access | Cross-site reachability to C1DC1 | C1DC1 | Prove Site 2 admin tooling can still reach the Site 1 primary controller. | nc -zvw5 172.30.65.2 3389 | connection succeeded | TCP 3389 on 172.30.65.2 succeeded from the Ubuntu jump. | PASS | Confirms cross-site admin path is live.
SB1 | Hotseat 2 | Remote Access | Cross-site reachability to C1DC2 | C1DC2 | Prove Site 2 admin tooling can still reach the Site 1 secondary controller. | nc -zvw5 172.30.65.3 3389 | connection succeeded | TCP 3389 on 172.30.65.3 succeeded from the Ubuntu jump. | PASS | Confirms cross-site admin path is live.
SB1 | Hotseat 2 | Remote Access | Cross-site reachability to C1Web mirror | C1Web mirror on Site 2 | Prove Site 2 admin tooling can reach the internal Company 1 web mirror hosted on the Site 2 path. | nc -zvw5 172.30.65.162 443 | connection succeeded | TCP 443 on 172.30.65.162 succeeded from the Ubuntu jump. | PASS | Useful for internal HTTPS demo routing.
SB1 | Hotseat 2 | Remote Access | Cross-site reachability to C1LinuxClient | C1LinuxClient | Prove Site 2 admin tooling can reach the Company 1 Linux client across the inter-site path. | nc -zvw5 172.30.65.36 22 | connection succeeded | TCP 22 on 172.30.65.36 succeeded from the Ubuntu jump. | PASS | Cross-site Linux support path is live.
SB2 | Hotseat 1 | DNS | C1 mini-zone query on C2IdM1 | C2IdM1 | Show the c1.local mini-zone exists on the primary Company 2 DNS node. | samba-tool dns query 127.0.0.1 c1.local c1-webserver A -P | 172.30.64.162 and 172.30.65.162 returned | Primary node returned both Site 1 and Site 2 C1 web A records. | PASS | Confirms cross-tenant mini-zone state.
SB2 | Hotseat 1 | DNS | C1 mini-zone query on C2IdM2 | C2IdM2 | Show the c1.local mini-zone exists on the secondary Company 2 DNS node. | samba-tool dns query 127.0.0.1 c1.local c1-webserver A -P | 172.30.64.162 and 172.30.65.162 returned | Secondary node returned both Site 1 and Site 2 C1 web A records. | PASS | Confirms replication to the secondary node.
SB2 | Hotseat 1 | HTTPS | OPNsense internal management listener | OPNsense | Show the internal management plane responds on the approved interface. | curl -I http://172.30.65.177 nc -zvw5 172.30.65.177 53 | HTTP 403 and TCP 53 reachable | OPNsense returned HTTP/1.1 403 Forbidden and TCP 53 succeeded from the Ubuntu jump. | PASS | Management plane present without changing state.
SB2 | Hotseat 2 | DNS | Ubuntu jump DNS summary for the core internal web name | Ubuntu Jump | Show the preferred Linux admin vantage point resolves the core internal web name used in the main demo. | nslookup c1-webserver.c1.local | The internal Company 1 web name resolves with dual A records | Ubuntu jump resolved c1-webserver.c1.local successfully through the current internal DNS stack. | PASS | Primary read-only validation vantage point for the main demo.
SB2 | Hotseat 2 | HTTPS | Ubuntu jump HTTPS to C1 hostname | Ubuntu Jump | Show Company 1 internal HTTPS is healthy from the Site 2 admin path. | curl -k -I https://c1-webserver.c1.local | HTTP 200 | Hostname-based HTTPS to c1-webserver.c1.local returned HTTP/2 200. | PASS | Validated from the Ubuntu jump.
SB2 | Hotseat 2 | HTTPS | C1 mirror on the Site 2 path by hostname | C1 web mirror on Site 2 | Prove the Site 2-hosted Company 1 mirror also requires the correct hostname. | curl -k -I --resolve c1-webserver.c1.local:443:172.30.65.162 https://c1-webserver.c1.local | HTTP 200 from IIS | Pinned hostname test returned HTTP/2 200 from Microsoft-IIS/10.0. | PASS | Shows correct mirror behavior on the Site 2 path.
SB2 | Hotseat 2 | HTTPS | C1 mirror on the Site 2 path by raw IP | C1 web mirror on Site 2 | Show raw IP access no longer serves the Company 1 tenant page on the Site 2 path. | curl -k -I https://172.30.65.162 | HTTP 404 | Raw HTTPS IP returned HTTP/2 404 from Microsoft-HTTPAPI/2.0. | PASS | Confirms hostname-only access pattern.
SB3 | Hotseat 2 | Site-to-Site VPN | Shared repository SMB path from Ubuntu jump | Ubuntu Jump to S2Veeam | Prove the Ubuntu jump can still reach the Site 2 SMB backup path used during administration and troubleshooting. | nc -zvw5 172.30.65.180 445 | connection succeeded | TCP 445 on 172.30.65.180 succeeded from the Ubuntu jump. | PASS | Matches the approved internal validation path.
SB3 | Hotseat 2 | Site-to-Site VPN | Veeam management ports from Ubuntu jump | Ubuntu Jump to S2Veeam | Prove the main Veeam management ports are reachable from the preferred admin path. | nc -zvw5 172.30.65.180 9392 nc -zvw5 172.30.65.180 5985 nc -zvw5 172.30.65.180 10005 nc -zvw5 172.30.65.180 10006 | connections succeeded on all listed management and agent-control ports | TCP 9392, 5985, 10005, and 10006 all succeeded to 172.30.65.180 during the March 23 live validation. | PASS | Confirms management-plane and agent-control reachability without opening the console.
SB4 | Hotseat 1 | Replicated File Server | C2FS mounted data volume | C2FS | Show the file-service data disk is mounted on the expected path. | findmnt /mnt/c2_public mount ¦ grep /mnt/c2_public | /dev/sdb mounted rw on /mnt/c2_public | /dev/sdb was mounted read-write on /mnt/c2_public. | PASS | Current live storage presentation proof.
SB4 | Hotseat 1 | Replicated File Server | C2FS public/private directory state | C2FS | Show the published public and private roots exist on the mounted data volume. | ls -ld /mnt/c2_public ls -ld /mnt/c2_public/Public ls -ld /mnt/c2_public/Private | Directories present with expected ownership/permissions | /mnt/c2_public, Public, and Private were present with current production ownership and mode bits. | PASS | Read-only directory proof only; no content changes were made.
SB4 | Hotseat 1 | Replicated File Server | Site1 to Site2 sync log summary | C2FS | Show the current pull-based Site 1 to Site 2 sync completed successfully. | tail -n 12 /var/log/c2_site1_sync.log | Latest run ends with Sync completed successfully | Latest log showed Public pull, Private pull, and Sync completed successfully at 02:00. | PASS | Strong evidence of healthy replication.
SB4 | Hotseat 2 | Replicated File Server | C2 SMB share inventory | C2FS | Show the published SMB shares visible on the local host. | smbclient -L localhost -N | C2_Public present; authenticated proof for private share may require manual follow-up | Anonymous share listing showed C2_Public and IPC$. | REVIEW | Use an authenticated screenshot if the final document needs direct proof of the private share definition.
SB4 | Hotseat 2 | Replicated File Server | C2LinuxClient mount and fstab evidence | C2LinuxClient | Check whether the Linux client currently exposes persistent CIFS/NFS mount evidence in the non-interactive admin context. | findmnt -t cifs,nfs cat /etc/fstab | Either mounts are shown or the row is documented for manual follow-up | No CIFS/NFS entries and no share lines were returned in the current non-interactive read-only probe. | REVIEW | Best completed with an interactive client screenshot during the live walkthrough.
SB4 | Hotseat 2 | Replicated File Server | Per-user private share isolation on Linux client | C2LinuxClient | Confirm each user can access only their own private share path. | Interactive per-user session test on C2LinuxClient | Owner access works; non-owner access denied | Not executed in this read-only non-interactive pass. | REVIEW | Needs interactive screenshot evidence from employee1 and employee2 contexts.
SB5 | Hotseat 1 | VEEAM | S2Veeam network reachability baseline | S2Veeam | Show the main backup host is reachable on backup and management ports. | nc -zvw5 172.30.65.180 445 nc -zvw5 172.30.65.180 3389 nc -zvw5 172.30.65.180 9392 nc -zvw5 172.30.65.180 5985 nc -zvw5 172.30.65.180 10005 nc -zvw5 172.30.65.180 10006 | All requested ports reachable, including 10005 and 10006 | TCP 445, 3389, 9392, 5985, 10005, and 10006 all succeeded from the Ubuntu jump during the March 23 live validation. | PASS | Updated with the final live validation refresh.
SB5 | Hotseat 1 | VEEAM | Veeam jobs, repositories, and copy history | S2Veeam console | Show backup jobs, repository inventory, and recent copy success in the GUI. | Open Veeam console and review Jobs, Repositories, and History | Recent local and offsite jobs visible | GUI evidence not collected in this read-only CLI pass. | REVIEW | Add console screenshots for the final submission package.
SB5 | Hotseat 2 | Misc | MSP Windows jump final DNS order | Jump64 | Show the final Windows DNS client order used for cross-site demo resolution. | Open IPv4 Advanced DNS settings | Internal DNS servers shown in the agreed order | This was discussed and configured earlier, but no fresh GUI screenshot was collected in this pass. | REVIEW | Add one screenshot from the Windows jump network adapter settings.
SB5 | Hotseat 2 | Misc | MSP Ubuntu jump final resolver config | Ubuntu Jump | Show the final netplan or resolved configuration used for internal demo testing. | cat /etc/netplan/01-netcfg.yaml resolvectl status | Internal DNS plus search suffixes visible | Resolver behavior was validated successfully, but the config file screenshot should still be added to the final appendix. | REVIEW | Add one terminal screenshot for the documentation package.

## Hotseat Guide
Site 2 Service Block Demo Guide
Purpose: give each student a one-to-one checklist for the live Site 2 Service Block demo.
Hotseat 1 focuses on Company 2 core services, DNS/core HTTPS proof, storage, and Veeam.
Hotseat 2 focuses on cross-site validation, MSP jump paths, and final manual screenshot items.
Use the Checklist sheet during the demo. This version already includes the 2026-03-22 read-only validation results.
Success? dropdown values remain PASS, REVIEW, FAIL.
Service Block | Hotseat 1 focus | Hotseat 2 focus | Suggested menu option | Result meaning | Notes
1 | Company 2 remote access, DHCP, Samba AD, and Linux client resolver proof | Cross-site reachability to Company 1 infrastructure from the Site 2 admin path | Toolkit menu 1 or jump-host terminal sequence | PASS = required read-only evidence observed | Start with the Ubuntu jump because it is the most reliable vantage point
2 | Company 2 DNS zones, c1.local mini-zone, and core HTTPS proof | Ubuntu jump DNS/HTTPS validation and final screenshot follow-up items | Toolkit menu 2 | REVIEW = evidence needs a manual follow-up screenshot | Keep the live demo on the main internal proof path rather than value-add web items
3 | Site 2 OPNsense internal management responses and VPN-backed service paths | Shared repository and Veeam management reachability from the Ubuntu jump | Toolkit menu 3 | FAIL = required evidence missing or blocked | Use rule and route evidence instead of value-add web hardening details
4 | C2FS mount state, public/private roots, and sync log proof | C2 Linux client share-consumption and private-share isolation follow-up | Toolkit menu 4 | Manual adjunct rows should still be demonstrated | Use screenshots for any interactive per-user share proof
5 | S2Veeam reachability and backup-console follow-up items | Final appendix captures and post-demo value-add follow-up items | Toolkit menu 5 | Students can also use a full end-to-end smoke test if time allows | Keep the screenshot list ready so REVIEW rows can be closed efficiently