## Checklist
Site 2 Service Block Demo Checklist
Use this sheet during the live demo. Each row maps to one test item from the current Site 2 Service Block flow.
Observed Test Result and Success? reflect the latest validated state as of 2026-03-25. Suggested values for Success?: PASS / REVIEW / FAIL.
Service Block | Hotseat | Area | Test Item | Device / Target | Purpose | Command / Action | Expected Result / Success Criteria | Observed Test Result | Success? | Notes
SB1 | Hotseat 1 | Remote Access | Approved RDP path to Jump64 | Jump64 | Prove controlled Windows administrative entry to the Site 2 management plane. | Use the approved remote path to Jump64 | Administrative access available | Administrative access confirmed | PASS | Keep the access method abstracted in the final demo wording.
SB1 | Hotseat 1 | Remote Access | Approved SSH path to MSPUbuntuJump | MSPUbuntuJump | Prove the primary Linux bastion is available for Site 2 validation work. | Use the approved SSH path to MSPUbuntuJump | Administrative access available | SSH access confirmed to mspubuntujump | PASS | Primary CLI validation path.
SB1 | Hotseat 1 | Remote Access | OPNsense management-plane HTTP response | RP-S2-Gateway | Show the firewall management plane responds on the expected internal address. | curl -I http://172.30.65.177 | HTTP response returned | HTTP 403 Forbidden returned | PASS | Confirms GUI presence without anonymous access.
SB1 | Hotseat 1 | Remote Access | OPNsense management-plane DNS port | RP-S2-Gateway | Show the routed management plane exposes DNS service on the expected address. | nc -zvw5 172.30.65.177 53 | Connection succeeds | TCP 53 succeeded | PASS | Supports the segmentation narrative.
SB1 | Hotseat 1 | Remote Access | C1DC1 administrative service set from MSP | C1DC1 | Show Site 2 management can reach the primary Company 1 infrastructure node. | nc -zvw5 172.30.65.2 53 88 389 445 3389 5985 | All required ports respond | 53/88/389/445/3389/5985 succeeded | PASS | Primary Company 1 DC reachable from MSP management path.
SB1 | Hotseat 1 | Remote Access | C1DC2 administrative service set from MSP | C1DC2 | Show Site 2 management can reach the secondary Company 1 infrastructure node. | nc -zvw5 172.30.65.3 53 88 389 445 3389 5985 | All required ports respond | 53/88/389/445/3389/5985 succeeded | PASS | Secondary Company 1 DC reachable from MSP management path.
SB1 | Hotseat 1 | Remote Access | C1FS administrative reachability from MSP | C1FS | Show the Company 1 file-service node remains reachable from Site 2 management. | nc -zvw5 172.30.65.4 445 3389 | Expected management/file ports respond | 445 and 3389 succeeded | PASS | WinRM was not part of the final success criterion for this row.
SB1 | Hotseat 1 | Remote Access | C1WindowsClient RDP reachability from MSP | C1WindowsClient | Show the Company 1 Windows client is reachable from the management plane. | nc -zvw5 172.30.65.11 3389 | Connection succeeds | TCP 3389 succeeded | PASS | Supports Company 1 endpoint reachability.
SB1 | Hotseat 1 | Remote Access | C1UbuntuClient SSH reachability from MSP | C1UbuntuClient | Show the Company 1 Linux client path is available from MSP management. | nc -zvw5 172.30.65.36 22 | Connection succeeds | TCP 22 succeeded | PASS | Client-side Company 1 Linux path available.
SB1 | Hotseat 1 | Remote Access | C1WebServer administrative and web reachability | C1WebServer | Show the Company 1 web node is both supportable and reachable over HTTPS. | nc -zvw5 172.30.65.162 443 3389 5985 | Expected ports respond | 443/3389/5985 succeeded | PASS | Company 1 web tier remains visible from Site 2.
SB1 | Hotseat 1 | HTTPS | Company 1 hostname-only HTTPS behavior | c1-webserver.c1.local | Show the Company 1 web service is consumed by hostname and not by raw IP. | curl -k -I https://c1-webserver.c1.local && curl -k -I https://172.30.65.162 | Hostname returns 200 and raw IP is rejected or non-site content | Hostname returned 200 and raw IP returned 404 | PASS | Matches the intended hostname-based publishing model.
SB1 | Hotseat 2 | Remote Access | SSH to C2IdM1 | C2IdM1 | Show the primary Company 2 identity node is reachable. | nc -zvw5 172.30.65.66 22 | Connection succeeds | TCP 22 succeeded | PASS | Primary C2 identity node reachable.
SB1 | Hotseat 2 | Remote Access | SSH to C2IdM2 | C2IdM2 | Show the secondary Company 2 identity node is reachable. | nc -zvw5 172.30.65.67 22 | Connection succeeds | TCP 22 succeeded | PASS | Secondary C2 identity node reachable.
SB1 | Hotseat 2 | Remote Access | SSH to C2FS | C2FS | Show the Company 2 file-service node is reachable. | nc -zvw5 172.30.65.68 22 | Connection succeeds | TCP 22 succeeded | PASS | Primary file-service validation path.
SB1 | Hotseat 2 | Remote Access | SSH to C2LinuxClient | C2LinuxClient | Show the Company 2 Linux client is reachable. | nc -zvw5 172.30.65.70 22 | Connection succeeds | TCP 22 succeeded | PASS | Client validation path available.
SB1 | Hotseat 2 | Remote Access | HTTPS to C2WebServer | C2WebServer | Show the Company 2 web tier is reachable over HTTPS. | nc -zvw5 172.30.65.170 443 | Connection succeeds | TCP 443 succeeded | PASS | Web path available before hostname-level tests.
SB1 | Hotseat 2 | Remote Access | S2Veeam management path from MSP | S2Veeam | Show the backup platform is reachable from the MSP bastion. | nc -zvw5 172.30.65.180 445 3389 9392 5985 10005 10006 | All required backup-management ports respond | 445/3389/9392/5985/10005/10006 succeeded | PASS | Covers SMB, RDP, Veeam console, WinRM, and agent ports.
SB2 | Hotseat 1 | DHCP | C2 DHCP failover primary summary | C2IdM1 | Show Company 2 DHCP failover is active on the primary node. | systemctl is-active isc-dhcp-server && grep -n "failover peer\¦primary;\¦subnet 172.30.65.64" /etc/dhcp/dhcpd.conf | DHCP service active and primary failover stanza present | DHCP active; failover peer and primary stanza present | PASS | Subnet 172.30.65.64/26 confirmed on primary.
SB2 | Hotseat 1 | DHCP | C2 DHCP failover secondary summary | C2IdM2 | Show Company 2 DHCP failover is active on the secondary node. | systemctl is-active isc-dhcp-server && grep -n "failover peer\¦secondary;\¦subnet 172.30.65.64" /etc/dhcp/dhcpd.conf | DHCP service active and secondary failover stanza present | DHCP active; failover peer and secondary stanza present | PASS | Subnet 172.30.65.64/26 confirmed on secondary.
SB2 | Hotseat 1 | Account Administration | C2 Samba user inventory | C2IdM1 | Show the required Company 2 user accounts are present. | samba-tool user list | Administrator, admin, employee1, and employee2 present | Administrator, admin, employee1, and employee2 present | PASS | Current list also includes Guest and krbtgt as expected.
SB2 | Hotseat 1 | Account Administration | C2 Samba group inventory | C2IdM1 | Show the required Company 2 groups are present. | samba-tool group list | c2_file_users and standard administrative groups present | c2_file_users plus standard administrative groups present | PASS | Supports public/private share access control.
SB2 | Hotseat 1 | DNS | C2IdM1 authoritative zone set | C2IdM1 | Show the Company 2 identity primary node hosts the required zones. | samba-tool dns zonelist 127.0.0.1 -P | c2.local, c1.local, and _msdcs.c2.local present | All three required zones present as primary zones | PASS | Confirms cross-tenant namespace is hosted on C2 DNS.
SB2 | Hotseat 1 | DNS | C2IdM2 authoritative zone set | C2IdM2 | Show the Company 2 identity secondary node hosts the required zones. | samba-tool dns zonelist 127.0.0.1 -P | c2.local, c1.local, and _msdcs.c2.local present | All three required zones present as primary zones | PASS | Secondary node mirrors the same DNS scope.
SB2 | Hotseat 1 | DNS | Company 1 web records on C2IdM1 | C2IdM1 | Show Company 1 web DNS records are hosted on the C2 DNS platform. | samba-tool dns query 127.0.0.1 c1.local c1-webserver A -P | Dual A records present | 172.30.64.162 and 172.30.65.162 present | PASS | Matches dual-site web publishing design.
SB2 | Hotseat 1 | DNS | Company 2 web records on C2IdM1 | C2IdM1 | Show Company 2 web DNS records are hosted on the C2 DNS platform. | samba-tool dns query 127.0.0.1 c2.local c2-webserver A -P | Dual A records present | 172.30.64.170 and 172.30.65.170 present | PASS | Confirms both site addresses are published.
SB2 | Hotseat 1 | DNS | Company 1 web records on C2IdM2 | C2IdM2 | Show the secondary C2 DNS node holds the same Company 1 web records. | samba-tool dns query 127.0.0.1 c1.local c1-webserver A -P | Dual A records present | 172.30.64.162 and 172.30.65.162 present | PASS | Replication state consistent on secondary node.
SB2 | Hotseat 1 | DNS | Company 2 web records on C2IdM2 | C2IdM2 | Show the secondary C2 DNS node holds the same Company 2 web records. | samba-tool dns query 127.0.0.1 c2.local c2-webserver A -P | Dual A records present | 172.30.64.170 and 172.30.65.170 present | PASS | Replication state consistent on secondary node.
SB2 | Hotseat 2 | Account Administration | C2LinuxClient realm membership | C2LinuxClient | Show the Linux client remains joined to the Company 2 domain. | realm list | c2.local kerberos-member present | c2.local kerberos-member present | PASS | SSSD-backed AD member state healthy.
SB2 | Hotseat 2 | Account Administration | C2LinuxClient user identity contexts | C2LinuxClient | Show the client resolves the required user identities and can assume them locally. | getent passwd admin; getent passwd employee1@c2.local; getent passwd employee2@c2.local; sudo -u employee1@c2.local whoami; sudo -u employee2@c2.local whoami | admin plus employee1 and employee2 identities available | admin, employee1, and employee2 identities resolved; sudo user context worked | PASS | Home directories already created for the domain users.
SB2 | Hotseat 2 | DNS | C2LinuxClient resolver domains | C2LinuxClient | Show the client now resolves both company namespaces without raw IP shortcuts. | nmcli connection show netplan-ens18 ¦ grep ipv4.dns-search; resolvectl status | Resolver includes c1.local and c2.local | dns-search c1.local,c2.local and resolvectl shows both domains | PASS | This was corrected and revalidated on 2026-03-25.
SB2 | Hotseat 2 | DNS | C2LinuxClient Company 1 hostname resolution | C2LinuxClient | Show the Company 1 web hostname resolves through the local stub resolver. | nslookup c1-webserver.c1.local | Dual A records returned | 172.30.64.162 and 172.30.65.162 returned | PASS | No raw IP override was added on the client.
SB2 | Hotseat 2 | DNS | C2LinuxClient Company 2 hostname resolution | C2LinuxClient | Show the Company 2 web hostname resolves through the local stub resolver. | nslookup c2-webserver.c2.local | Dual A records returned | 172.30.64.170 and 172.30.65.170 returned | PASS | Confirms resolver symmetry.
SB2 | Hotseat 2 | HTTPS | C2LinuxClient to Company 1 website | C2LinuxClient -> c1-webserver.c1.local | Show the C2 client can consume the Company 1 site by hostname only. | curl -skI https://c1-webserver.c1.local | HTTP 200 returned | HTTP/2 200 returned | PASS | Cross-company hostname path validated from the client.
SB2 | Hotseat 2 | HTTPS | C2LinuxClient to Company 2 website | C2LinuxClient -> c2-webserver.c2.local | Show the C2 client can consume the Company 2 site by hostname only. | curl -skI https://c2-webserver.c2.local | HTTP 200 returned | HTTP/1.1 200 OK returned | PASS | Same client validates both internal web identities.
SB2 | Hotseat 2 | HTTPS | C2WebServer nginx service and server_name | C2WebServer | Show the Company 2 web tier is explicitly bound to the tenant hostname. | systemctl is-active nginx && grep -R "server_name" /etc/nginx/sites-enabled /etc/nginx/conf.d | nginx active and c2-webserver.c2.local server_name present | nginx active; c2web config includes c2-webserver.c2.local | PASS | Host-header-driven site binding confirmed.
SB2 | Hotseat 2 | HTTPS | C2WebServer local hostname-only behavior | C2WebServer | Show local host-header access succeeds while raw IP does not map to the site. | curl -skI -H "Host: c2-webserver.c2.local" https://127.0.0.1 && curl -skI https://127.0.0.1 | Hostname returns 200 and raw IP returns non-site response | Hostname returned 200 and raw IP returned 404 | PASS | Matches the intended vhost security posture.
SB3 | Hotseat 1 | Replicated File Server | C2FS SMB service state | C2FS | Show the Company 2 file-service daemon is healthy. | systemctl is-active smbd | active | active | PASS | Primary SMB daemon healthy.
SB3 | Hotseat 1 | ISCSI | C2FS iSCSI initiator daemon | C2FS | Show the iSCSI initiator service is running on the file-service node. | systemctl is-active iscsid | active | active | PASS | Prerequisite for SAN-backed storage delivery.
SB3 | Hotseat 1 | ISCSI | C2FS active iSCSI session | C2FS | Show the file-service node has an active session to the C2 SAN target. | iscsiadm -m session | Active session to 172.30.65.194:3260 | Active session to iqn.2024-03.org.clearroots:c2san at 172.30.65.194:3260 | PASS | Confirms SAN transport is live.
SB3 | Hotseat 1 | Replicated File Server | C2FS mounted data volume | C2FS | Show the SAN-backed volume is mounted for share presentation. | findmnt /mnt/c2_public | Mounted volume visible | /dev/sdb mounted at /mnt/c2_public | PASS | Mounted data disk is the live share backing store.
SB3 | Hotseat 1 | Replicated File Server | C2FS public share definition | C2FS | Show the public share points to the expected path and group model. | testparm -s ¦ grep -A6 "^\[C2_Public\]" | C2_Public points to /mnt/c2_public/Public | C2_Public maps to /mnt/c2_public/Public with c2_file_users access | PASS | Public share path and access model confirmed.
SB3 | Hotseat 1 | Replicated File Server | C2FS private share definition | C2FS | Show the private share uses per-user path mapping. | testparm -s ¦ grep -A6 "^\[C2_Private\]" | C2_Private points to /mnt/c2_public/Private/%U | C2_Private maps to /mnt/c2_public/Private/%U | PASS | Private share isolation is path-driven on the server side.
SB3 | Hotseat 1 | Replicated File Server | C2FS private directory tree | C2FS | Show server-side private directories exist for the expected users. | find /mnt/c2_public -maxdepth 2 -type d ¦ sort | Public and Private trees visible with per-user folders | Private folders present for admin, admindc, employee1, employee2, user1, and user2 | PASS | Server-side private-share layout already exists.
SB3 | Hotseat 1 | Replicated File Server | C2FS synchronization log | C2FS | Show the most recent sync completed successfully. | tail -n 15 /var/log/c2_site1_sync.log | Recent successful completion visible | 2026-03-25 02:00 start and successful completion visible | PASS | Confirms current sync health.
SB3 | Hotseat 2 | Replicated File Server | C2LinuxClient hostname resolution for C2FS | C2LinuxClient | Show the client can reach the file server by name rather than by raw IP. | getent hosts c2fs.c2.local | c2fs.c2.local resolves | 172.30.65.68 returned for c2fs.c2.local | PASS | Supports name-based SMB validation.
SB3 | Hotseat 2 | Replicated File Server | C2LinuxClient SMB browse by hostname as employee1 | C2LinuxClient -> c2fs.c2.local | Show authenticated SMB browse succeeds using the file-server hostname. | smbclient -L //c2fs.c2.local -W C2 -U employee1%Cisco123! | Share browse succeeds | SMB browse succeeded and listed C2_Public | PASS | Hostname-based SMB path works without raw IP.
SB3 | Hotseat 2 | Replicated File Server | C2LinuxClient public share access as employee1 | C2LinuxClient -> C2_Public | Show employee1 can browse the public Company 2 share. | smbclient //c2fs.c2.local/C2_Public -W C2 -U employee1%Cisco123! -c ls | Directory listing succeeds | Public share listing returned expected files | PASS | Public share consumed by hostname.
SB3 | Hotseat 2 | Replicated File Server | C2LinuxClient private share access as employee1 | C2LinuxClient -> C2_Private | Show employee1 reaches the employee1 private view of C2_Private. | smbclient //c2fs.c2.local/C2_Private -W C2 -U employee1%Cisco123! -c ls | Directory listing succeeds | employee1 private listing returned employee1 content | PASS | Per-user private path works for employee1.
SB3 | Hotseat 2 | Replicated File Server | C2LinuxClient private share access as employee2 | C2LinuxClient -> C2_Private | Show employee2 reaches the employee2 private view of C2_Private. | smbclient //c2fs.c2.local/C2_Private -W C2 -U employee2%Cisco123! -c ls | Directory listing succeeds | employee2 private listing returned employee2 content | PASS | Per-user private path works for employee2.
SB3 | Hotseat 2 | Replicated File Server | C2LinuxClient public write/delete workflow as employee1 | C2LinuxClient -> C2_Public | Show a standard user can create and remove a temporary file in the public share. | smbclient //c2fs.c2.local/C2_Public -W C2 -U employee1%Cisco123! -c "put ...; ls ...; del ..." | Temporary file create/list/delete succeeds | Temporary file upload, listing, and deletion all succeeded | PASS | Confirms practical public-share write access.
SB4 | Hotseat 1 | VEEAM | S2Veeam port set from MSP | S2Veeam | Show the backup platform is reachable on all required management and data ports. | nc -zvw5 172.30.65.180 445 3389 9392 5985 10005 10006 | All required ports respond | 445/3389/9392/5985/10005/10006 succeeded | PASS | Port-level backup path validated.
SB4 | Hotseat 1 | VEEAM | S2Veeam repositories and offsite target (GUI) | S2Veeam | Show the local Site 2 repository and the Site 1 offsite SMB target in the Veeam console. | Open Backup Infrastructure > Backup Repositories | Site2Veeam and Site1OffsiteSmbShare visible | Latest GUI evidence shows Site2Veeam and Site1OffsiteSmbShare; refresh screenshot after credential change | REVIEW | Use the refreshed Veeam screenshot set in the final demo pack.
SB4 | Hotseat 1 | VEEAM | S2Veeam backup job inventory (GUI) | S2Veeam | Show the current backup-job set for file shares and server groups. | Open Home > Jobs > Backup | C1_FileShare, C2_FileShare, Ubuntu_Servers, and Windows_Servers visible | Latest GUI evidence shows expected jobs; refresh screenshot after credential change | REVIEW | Row remains operationally valid, but GUI proof should be refreshed.
SB4 | Hotseat 1 | VEEAM | S2Veeam backup-copy inventory (GUI) | S2Veeam | Show the offsite copy jobs toward Site 1 are present. | Open Home > Jobs > Backup Copy | File-share and server offsite copy jobs visible | Latest GUI evidence shows expected copy jobs; refresh screenshot after credential change | REVIEW | Refresh the GUI evidence with the current Veeam login context.
SB5 | Hotseat 2 | Platform Baseline | Site 2 Linux VM and service baseline summary | C2IdM1 / C2IdM2 / C2FS / C2LinuxClient / C2WebServer | Show the current Linux VM platform baseline for the Site 2 environment. | hostnamectl; nproc; free -h; lsblk; systemctl list-units --type=service --state=running | VM roles, OS versions, and service roles align to the documented design | All core Linux VMs are KVM/QEMU guests with 4 vCPU; IdM/FS/Web run Ubuntu 22.04.5 LTS and C2LinuxClient runs Ubuntu 25.04 | PASS | Useful for the technical report hardware/platform appendix.
SB5 | Hotseat 2 | Platform Baseline | C2FS network and data-disk baseline | C2FS | Show the file-service node keeps management and SAN traffic separate and presents a dedicated data disk. | ip -4 addr show; lsblk -o NAME,SIZE,FSTYPE,MOUNTPOINT | Service NIC, SAN NIC, and mounted data disk all visible | C2FS shows 172.30.65.68/26 service NIC, 172.30.65.195/29 SAN NIC, and 160G /dev/sdb mounted at /mnt/c2_public | PASS | This row captures the storage-adjacent hardware shape of the service.

## Hotseat Guide
Site 2 Service Block Demo Guide
Purpose: give each student a one-to-one checklist for the live Site 2 Service Block demo.
Hotseat 1 focuses on MSP entry, Company 1 cross-site service paths, DHCP/DNS control points, and Veeam.
Hotseat 2 focuses on Company 2 identity, hostname-based web delivery, file services, client access, and VM/service baseline.
Use the Checklist sheet during the demo. The latest observed results are pre-filled and can be reconfirmed live.
Success? values: PASS, REVIEW, FAIL. REVIEW is used only where refreshed GUI evidence is still pending.
Service Block | Hotseat 1 focus | Hotseat 2 focus | Suggested menu option | Result meaning | Notes
1 | MSP entry, OPNsense presence, Company 1 reachability, and Company 1 hostname-only HTTPS | Company 2 reachability plus S2Veeam path confirmation | Checklist SB1 | PASS = required evidence observed | Run top-to-bottom per hotseat
2 | C2 DHCP failover, Samba users/groups, and DNS zone ownership | C2LinuxClient resolver, dual-hostname web validation, and C2 nginx checks | Checklist SB2 | REVIEW = GUI or manual refresh still needed | This block contains the corrected C2LinuxClient DNS behavior
3 | C2FS iSCSI, mounted storage, share definitions, and sync health | Hostname-based SMB browse, public write, and private-share access from C2LinuxClient | Checklist SB3 | FAIL = required evidence missing or blocked | Name-based share validation replaces raw-IP testing
4 | S2Veeam management ports plus repository, job, and backup-copy walkthrough | Support Hotseat 1 if the Veeam console is challenged | Checklist SB4 | REVIEW rows should be refreshed with the current Veeam login | Keep the updated Veeam screenshots ready
5 | Support Hotseat 2 with platform and service-baseline walkthrough | Show C2FS dual-NIC plus SAN-backed data-disk model | Checklist SB5 | Use this block to enrich the technical explanation | Useful when the marker asks why the design is laid out this way