## Test Matrix
Site 2 Source-Based Test Document
Built from the provided course documents, the OPNsense export, user-supplied Site 2 evidence, and live read-only validation on 2026-03-23.
Phase No | Source (Device) | Destination | Connectivity | Service / Protocol | Test Command | Expected Result | Observed Result | Status | Comment
1.1 | Local Workstation | Windows Jump | Tailscale | RDP | Test TCP 100.97.37.83:3389 | TCP reachable | Reachable from local workstation | PASS | Primary GUI bastion path.
1.2 | Local Workstation | Ubuntu Jump | Tailscale | SSH | Test TCP 100.82.97.92:22 | TCP reachable | Reachable from local workstation | PASS | Primary CLI bastion path.
1.3 | Local Workstation | Teacher Edge -> Windows Jump | Published Port | RDP | Test TCP 10.50.17.31:33464 | TCP reachable | Reachable from local workstation | PASS | Teacher-edge jump access healthy.
1.4 | Local Workstation | Teacher Edge -> Ubuntu Jump | Published Port | SSH | Test TCP 10.50.17.31:33564 | TCP reachable | Reachable from local workstation | PASS | Teacher-edge jump access healthy.
2.1 | OPNsense XML | Interface Set | Config Review | Network Segmentation | Review exported interfaces | MSP, C1LAN, C1DMZ, C2LAN, C2DMZ, WAN, and SITE1_OVPN visible | All required interfaces present in export | PASS | Segmentation is evidence-based, not inferred.
2.2 | OPNsense XML | Published Edge Services | Config Review | WAN NAT | Review WAN NAT rules | Only jump-host publications visible | 33464 -> Jump64 RDP and 33564 -> MSPUbuntuJump SSH visible | PASS | Matches bastion-first design.
2.3 | Ubuntu Jump | OPNsense | HTTP | Firewall Management | curl -I http://172.30.65.177 | Management plane responds | HTTP 403 Forbidden returned | PASS | Shows the GUI exists without anonymous exposure.
2.4 | Ubuntu Jump | OPNsense | TCP | DNS / Management Plane | nc -zvw5 172.30.65.177 53 | Connection succeeds | TCP 53 succeeded | PASS | Confirms routed management-plane presence.
2.5 | OPNsense XML | OpenVPN Policy | Config Review | Inter-site Rules | Review OpenVPN, DNS, web, and Veeam rules | Cross-site rules visible for C1, C2, and Veeam | Rules visible for C1_REMOTE, C2_REMOTE, SITE1_VEEAM, ALL_DNS, and cross-site web access | PASS | Explains how Site 1 and Site 2 interact.
3.1 | Ubuntu Jump | C1DC1 | TCP | RDP | nc -zvw5 172.30.65.2 3389 | Connection succeeds | TCP 3389 succeeded | PASS | Company 1 remains reachable from Site 2.
3.2 | Ubuntu Jump | C1DC1 | TCP | SMB | nc -zvw5 172.30.65.2 445 | Connection succeeds | TCP 445 succeeded | PASS | Company 1 remains reachable from Site 2.
3.3 | Ubuntu Jump | C1DC2 | TCP | RDP | nc -zvw5 172.30.65.3 3389 | Connection succeeds | TCP 3389 succeeded | PASS | Second Company 1 DC reachable from Site 2.
3.4 | Ubuntu Jump | C1DC2 | TCP | SMB | nc -zvw5 172.30.65.3 445 | Connection succeeds | TCP 445 succeeded | PASS | Second Company 1 DC reachable from Site 2.
3.5 | Ubuntu Jump | C1FS | TCP | SMB | nc -zvw5 172.30.65.4 445 | Connection succeeds | TCP 445 succeeded | PASS | Cross-site file-service admin path healthy.
3.6 | Ubuntu Jump | S2-Ubuntu-Client | TCP | SSH | nc -zvw5 172.30.65.36 22 | Connection succeeds | TCP 22 succeeded | PASS | Company 1 client role reachable from Site 2.
4.1 | C2IdM1 | Local Services | Service State | Samba AD | systemctl is-active samba-ad-dc | active | active | PASS | Primary Company 2 identity node healthy.
4.2 | C2IdM2 | Local Services | Service State | Samba AD | systemctl is-active samba-ad-dc | active | active | PASS | Secondary Company 2 identity node healthy.
4.3 | C2IdM1 | Local Services | Service State | DHCP | systemctl is-active isc-dhcp-server | active | active | PASS | Company 2 DHCP service healthy.
4.4 | C2IdM2 | Local Services | Service State | DHCP | systemctl is-active isc-dhcp-server | active | active | PASS | Company 2 DHCP failover partner healthy.
4.5 | C2IdM1 | c1-webserver.c1.local | DNS | A Record Query | samba-tool dns query 127.0.0.1 c1.local c1-webserver A -P | Dual A records returned | 172.30.64.162 and 172.30.65.162 returned | PASS | Proves Company 1 exists in Site 2 DNS scope.
4.6 | C2IdM2 | c2-webserver.c2.local | DNS | A Record Query | samba-tool dns query 127.0.0.1 c2.local c2-webserver A -P | Dual A records returned | 172.30.64.170 and 172.30.65.170 returned | PASS | Replicated Company 2 DNS state healthy.
4.7 | User-Supplied Environment Detail | c1.local and c2.local | Design Basis | Shared Forest | Review supplied environment clarification | Cross-domain design explained | Shared forest stated by environment owner and consistent with live DNS behavior | PASS | Use a GUI screenshot if explicit forest proof is requested.
5.1 | S2-Ubuntu-Client | C1 Domain | Identity | Realm Membership | hostnamectl; realm list | Host and realm visible | S2-Ubuntu-Client in C1.LOCAL context | PASS | Confirms the Company 1 client role.
5.2 | S2-Ubuntu-Client | c1-webserver.c1.local | DNS | Name Resolution | nslookup c1-webserver.c1.local | Dual A records returned | 172.30.65.162 and 172.30.64.162 returned | PASS | Company 1 client resolves Company 1 web.
5.3 | S2-Ubuntu-Client | c2-webserver.c2.local | DNS | Name Resolution | nslookup c2-webserver.c2.local | Dual A records returned | 172.30.65.170 and 172.30.64.170 returned | PASS | Company 1 client resolves Company 2 web.
5.4 | S2-Ubuntu-Client | c1-webserver.c1.local | HTTPS | Hostname Validation | curl -k -I https://c1-webserver.c1.local | HTTP 200 | HTTP/2 200 returned | PASS | Company 1 client reaches Company 1 web by hostname.
5.5 | S2-Ubuntu-Client | c2-webserver.c2.local | HTTPS | Hostname Validation | curl -k -I https://c2-webserver.c2.local | HTTP 200 | HTTP/1.1 200 OK returned | PASS | Company 1 client reaches Company 2 web by hostname.
6.1 | C2LinuxClient | C2 Domain | Identity | Realm Membership | realm list | C2.LOCAL membership visible | Realm membership present | PASS | Client remains joined to the domain.
6.2 | C2LinuxClient | employee1@c2.local | Identity | SSSD / NSS | getent passwd employee1@c2.local | User record returned | Valid passwd entry returned | PASS | Domain-user lookup works.
6.3 | C2LinuxClient | employee2@c2.local | Identity | SSSD / NSS | getent passwd employee2@c2.local | User record returned | Valid passwd entry returned | PASS | Domain-user lookup works.
6.4 | C2LinuxClient | c1-webserver.c1.local | HTTPS | Hostname Validation | curl -k -I https://c1-webserver.c1.local | HTTP 200 | HTTP/2 200 returned | PASS | Company 2 client reaches Company 1 web by hostname.
6.5 | C2LinuxClient | c2-webserver.c2.local | HTTPS | Hostname Validation | curl -k -I https://c2-webserver.c2.local | HTTP 200 | HTTP/1.1 200 OK returned | PASS | Company 2 client reaches Company 2 web by hostname.
6.6 | C2LinuxClient | Local Mount Table | Read-Only Review | CIFS / NFS Presentation | findmnt -t cifs,nfs; cat /etc/fstab | Mounted share evidence visible or follow-up documented | No persistent CIFS/NFS lines visible in current non-interactive context | REVIEW | Use an interactive screenshot during the final demo if share presentation is required.
7.1 | C2FS | Local Services | Service State | SMB | systemctl is-active smbd | active | active | PASS | File service daemon healthy.
7.2 | C2FS | /mnt/c2_public | Mounted Storage | EXT4 Volume | findmnt /mnt/c2_public | Mounted volume visible | Mounted from /dev/sdb | PASS | Company 2 file-service data volume present.
7.3 | C2FS | 172.30.65.194:3260 | iSCSI | SAN Session | iscsiadm -m session | Active iSCSI session visible | Active session to iqn.2024-03.org.clearroots:c2san | PASS | Required SAN evidence present.
7.4 | C2FS | C2_Public | SMB | Share Definition | testparm -s | Share definition visible | [C2_Public] defined for /mnt/c2_public/Public | PASS | Public share configuration present.
7.5 | C2FS | C2_Private | SMB | Share Definition | testparm -s | Share definition visible | [C2_Private] defined for /mnt/c2_public/Private/%U | PASS | Private per-user share configuration present.
7.6 | C2FS | Site1 -> Site2 Sync | Cross-Site Sync | Replication Log | tail -n 15 /var/log/c2_site1_sync.log | Latest run ends successfully | Latest log ended with Sync completed successfully | PASS | Cross-site file synchronization healthy.
7.7 | User-Supplied SAN Screenshots | C1SAN and C2SAN | Evidence Review | Isolated Storage Design | Review supplied interface screenshots | Dedicated SAN interfaces visible | C1SAN at 172.30.65.186/29 and C2SAN at 172.30.65.194/29 recorded | PASS | Supports isolated bridge-to-FS storage design.
8.1 | Ubuntu Jump | Company 1 Web on Site 2 Path | HTTPS | Hostname Validation | curl -k -I --resolve c1-webserver.c1.local:443:172.30.65.162 https://c1-webserver.c1.local | HTTP 200 | HTTP/2 200 returned | PASS | Company 1 internal web reachable by hostname on Site 2 path.
8.2 | Ubuntu Jump | 172.30.65.162 | HTTPS | Raw IP Hardening | curl -k -I https://172.30.65.162 | HTTP 404 or hardened response | HTTP/2 404 returned | PASS | Hostname-only publishing behavior confirmed.
8.3 | Ubuntu Jump | Company 2 Web on Site 2 Path | HTTPS | Hostname Validation | curl -k -I --resolve c2-webserver.c2.local:443:172.30.65.170 https://c2-webserver.c2.local | HTTP 200 | HTTP/1.1 200 OK returned | PASS | Company 2 internal web reachable by hostname on Site 2 path.
8.4 | Ubuntu Jump | 172.30.65.170 | HTTPS | Raw IP Hardening | curl -k -I https://172.30.65.170 | HTTP 404 or hardened response | HTTP/1.1 404 Not Found returned | PASS | Hostname-only publishing behavior confirmed.
9.1 | Ubuntu Jump | S2Veeam | TCP | SMB | nc -zvw5 172.30.65.180 445 | Connection succeeds | TCP 445 succeeded | PASS | Backup host reachable.
9.2 | Ubuntu Jump | S2Veeam | TCP | RDP | nc -zvw5 172.30.65.180 3389 | Connection succeeds | TCP 3389 succeeded | PASS | Backup host reachable for GUI access.
9.3 | Ubuntu Jump | S2Veeam | TCP | Veeam Console / API | nc -zvw5 172.30.65.180 9392 | Connection succeeds | TCP 9392 succeeded | PASS | Primary Veeam management path reachable.
9.4 | Ubuntu Jump | S2Veeam | TCP | WinRM / Remote Management | nc -zvw5 172.30.65.180 5985 | Connection succeeds | TCP 5985 succeeded | PASS | Remote management path reachable.
9.5 | Ubuntu Jump | S2Veeam | TCP | Agent Control | nc -zvw5 172.30.65.180 10005 | Connection succeeds | TCP 10005 succeeded | PASS | Agent-control path reachable.
9.6 | Ubuntu Jump | S2Veeam | TCP | Agent Control | nc -zvw5 172.30.65.180 10006 | Connection succeeds | TCP 10006 succeeded | PASS | Agent-control path reachable.
9.7 | OPNsense XML and User-Supplied Backup Detail | Site 1 / Site 2 Veeam Flow | Design Review | Backup Architecture | Review VEEAM_COPY_PORTS, static route, and environment clarification | Site 2 disk, file-share backup, and Site 1 offsite relationship documented | 10 protected machines plus file-share backup and offsite-copy intent documented | PASS | Close with a Veeam GUI screenshot in final submission.

## Demo Scenarios
Scenario | Why It Is Likely In Demo | Best Validation Path | What To Show | Current State
Secure entry to Site 2 | Jump-box strategy is emphasized in class notes and Service Blocks | Local workstation -> Windows or Ubuntu jump | RDP or SSH access to jump host | Ready
OPNsense segmentation proof | The XML export allows the team to explain design decisions instead of only live pings | OPNsense XML plus one GUI screenshot | Interfaces, NAT, aliases, and OpenVPN rules | Ready
Company 2 identity proof | Project requires AD/LDAP, DNS, DHCP, and client onboarding | Ubuntu jump -> C2IdM1 / C2IdM2 | Samba AD active, DHCP active, DNS records visible | Ready
Company 1 still visible in Site 2 | Service Blocks split both companies across hotseats | Ubuntu jump -> Company 1 paths | Cross-site reachability and Company 1 web on Site 2 path | Ready
Storage and isolated SAN proof | Week 4 and Week 7 notes make iSCSI a likely check | Ubuntu jump -> C2FS plus SAN screenshots | iSCSI session, mount, share definitions, and SAN interfaces | Ready
Dual-client web proof | The user confirmed both sites use the same hostnames | S2-Ubuntu-Client and C2LinuxClient | Both clients reach both required hostnames | Ready
Backup and offsite protection | Service Block 5 is reserved for VEEAM and misc evidence | Ubuntu jump plus Veeam GUI | Port reachability plus Veeam repository and offsite-copy screenshot | Partially ready

## Source Basis
Source Document | How It Was Used
25F-Project (1).pdf | Defined Site 2 as the MSP public-cloud site and established Company 1, Company 2, storage, backup, and remote-access requirements.
Week 09 technical-report PDF | Defined the handover-style technical report structure and content expectations.
ServiceBlocks.pdf | Defined the hotseat and service-block logic showing both Company 1 and Company 2 in Site 2 demo scope.
Site1_Final_Documentation_V3.0.docx | Provided the final report structure, density, and handover style to mirror.
Site1_test_V0.1.xlsx | Provided the phased test-matrix style that this workbook adapts.
Week 3-7 notes | Provided instructor intent around bastion hosts, storage, iSCSI, Veeam, and demo preparation.
config-rp-msp-gateway.et.lab-20260323222847.xml | Provided real Site 2 interface, NAT, alias, route, and firewall evidence.
User-supplied Site 2 screenshots and clarifications | Provided the VM inventory, SAN IPs, Company 1 client mapping, shared-forest note, and Veeam design summary.
Live Site 2 validation | Supplied the actual observed results recorded in this workbook.

## Requirements Traceability
Requirement Area | Implementation in Site 2 | Primary Evidence | Status | Submission Note
Secure remote access | Jump64, MSPUbuntuJump, Tailscale path, teacher-edge path, OPNsense NAT only for jump services | Test Matrix 1.x-2.x, OPNsense XML | Proven | Open one jump host before demo starts.
Segmented networking | MSP, C1LAN, C1DMZ, C2LAN, C2DMZ, SITE1_OVPN, isolated SAN bridges | OPNsense XML plus SAN screenshots | Proven | Use one GUI firewall screenshot for faster explanation.
Site-to-site connectivity | OpenVPN path with C1_REMOTE, C2_REMOTE, and Veeam copy flow | OPNsense XML plus cross-site tests | Proven | Explain that Company 1 remains visible in Site 2.
Company 2 identity / DNS / DHCP | C2IdM1 and C2IdM2 | Test Matrix 4.x | Proven | Screenshots from both nodes will strengthen marking.
Company 1 and Company 2 web availability | c1-webserver.c1.local and c2-webserver.c2.local available from both clients | Test Matrix 5.x, 6.x, 8.x | Proven | Always demonstrate by hostname, not raw IP.
File services and share isolation | C2FS with C2_Public and C2_Private | Test Matrix 7.x | Proven | Interactive share screenshot still recommended.
iSCSI and SAN design | C2SAN -> C2FS plus isolated C1SAN and C2SAN bridges | Test Matrix 7.x and supplied SAN screenshots | Proven | Call out that storage is isolated from user LAN segments.
Backup, file-share backup, and offsite copy | S2Veeam with Site 2 disk and Site 1 offsite path | Test Matrix 9.x, OPNsense XML, supplied backup detail | Strongly supported | Close with one Veeam GUI screenshot.
Linux-client external SSH expectation | Administrative and internal path proven | Cross-site and client tests | Partially evidenced | If asked specifically about college-edge SSH, show live external proof or screenshot.

## Environment Inventory
VMID / Host | Hostname | IP / Network | Role | Company / Scope | Platform / OS | Notes
6401 | Jump64 | 172.30.65.178 | Windows jump | MSP | Windows VM | Published at teacher-edge 33464.
6402 | RP-S2-Gateway | 172.30.65.177 | Gateway / firewall | MSP | OPNsense | Segments MSP, C1, C2, DMZ, and VPN paths.
6403 | MSPUbuntuJump | 172.30.65.179 | CLI bastion | MSP | Ubuntu VM | Published at teacher-edge 33564.
6404 | S2Veeam | 172.30.65.180 | Backup / offsite copy server | MSP | Windows VM | User-supplied design says 10 machines plus file-share backup.
6410 | C1SAN | 172.30.65.186/29 | Isolated SAN | Company 1 | Windows / SAN role | Gateway 172.30.65.185 from supplied screenshot.
6411 | C1WebServer | 172.30.65.162 | Web server | Company 1 | Windows / IIS | Returns 200 by hostname and 404 by raw IP.
6413 | C1FS | 172.30.65.4 | File server | Company 1 | Windows VM | Cross-site reachable from Site 2.
6414 | C1DC1 | 172.30.65.2 | Domain controller | Company 1 | Windows VM | In ALL_DNS alias and cross-site tests.
6415 | C1DC2 | 172.30.65.3 | Domain controller | Company 1 | Windows VM | User clarified address directly.
6416 | C1WindowsClient | 172.30.65.11 | Windows client | Company 1 | Windows VM | Listed in supplied environment screenshot.
6417 | S2-Ubuntu-Client | 172.30.65.36 | Linux client role | Company 1 | Ubuntu VM | Clarified by user as the active Company 1 client role.
6421 | C2IdM1 | 172.30.65.66 | Identity / DNS / DHCP | Company 2 | Ubuntu / Samba AD | Healthy in live validation.
6422 | C2IdM2 | 172.30.65.67 | Identity / DNS / DHCP | Company 2 | Ubuntu / Samba AD | Healthy in live validation.
6423 | C2FS | 172.30.65.68 | File server | Company 2 | Ubuntu VM | Mounted iSCSI storage and share definitions confirmed.
6424 | C2LinuxClient | 172.30.65.70 | Linux client | Company 2 | Ubuntu VM | User lookup and dual-web proof confirmed.
6425 | C2WebServer | 172.30.65.170 | Web server | Company 2 | Ubuntu / Nginx | Returns 200 by hostname and 404 by raw IP.
6426 | C2SAN | 172.30.65.194/29 | Isolated SAN | Company 2 | Ubuntu / SAN role | Gateway 172.30.65.193 from supplied screenshot.

## Demo Runbook
Step | Console / System | Action | Key Point to Explain | Expected Result | Related Figure
1 | Local workstation | Open one jump path | Site 2 uses bastion-led entry instead of broad direct exposure | Jump host reachable | Figure 1 or Figure 3
2 | OPNsense | Show interfaces, NAT, aliases, and OpenVPN rules | Segmentation and limited edge exposure are intentional design choices | Clear routed design visible | Figure 3 or Figure 4
3 | C2IdM1 / C2IdM2 | Show AD, DHCP, and dual DNS records | Company 2 identity is healthy and Company 1 remains visible | Active services and A records | Figure 5, Figure 6, Figure 7
4 | Ubuntu jump | Show Company 1 cross-site reachability and Company 1 web success | Site 2 is not Company 2-only | Cross-site ports and Company 1 web path succeed | Figure 8
5 | S2-Ubuntu-Client | Show access to both required hostnames | Company 1 client can consume both hosted services | Two hostname successes | Figure 13
6 | C2LinuxClient | Show user lookup and access to both hostnames | Company 2 client and identity path are healthy | Valid user proof and two hostname successes | Figure 14
7 | C2FS and SAN evidence | Show iSCSI session, mount, shares, sync, and SAN screenshots | Storage is isolated and operational | Session, mount, and share proof visible | Figure 9, Figure 10, Figure 11, Figure 12
8 | S2Veeam | Show repository, protected machines, and offsite relationship | Recovery design is real, not theoretical | Repository and backup evidence visible | Figure 15

## Troubleshooting
Symptom | First Check | Healthy Sign | Likely Fault Domain | Fastest Evidence or Command
Cannot enter Site 2 | Jump hosts and published ports | Jump systems reachable | Edge exposure, Tailscale, or jump-host issue | Tailscale tests and Test Matrix 1.x
Hostname does not resolve | C2IdM1 / C2IdM2 DNS records | Dual A records returned | DNS record, replication, or resolver issue | samba-tool dns query / nslookup
Company 2 user lookup fails | C2LinuxClient realm and NSS | Realm present and getent returns user | SSSD, join, or identity-service issue | realm list / getent passwd
Shares unavailable | C2FS service, mount, and iSCSI session | smbd active, mount present, session visible | SMB service, mount, or SAN issue | systemctl / findmnt / iscsiadm / testparm
Web returns 404 by hostname | Client hostname used and DNS target correct | Hostname returns 200 while raw IP returns 404 | Wrong host header, DNS mismatch, or virtual-host issue | curl -k -I by hostname and raw IP
Company 1 path missing from Site 2 | Ubuntu jump cross-site reachability and OPNsense rules | Company 1 ports and hostname path succeed | OpenVPN, route, rule, or remote Company 1 issue | nc checks and XML rule review
Backup confidence is low | S2Veeam ports, route, and Veeam GUI | Ports reachable and repository visible | Veeam service, repository, or inter-site copy issue | Test Matrix 9.x and Veeam console